## Definitions
Lead Department
While many action steps involve cross-department coordination, this cell should identify the lead. If partnerships are key to success, the other departments can be listed within the action step
Timeframes
Short-Term | 0-5 years
Medium-Term | 6-10 years
Long-Term | 10+ years

## Action Steps
Theme | Action Number | Action | City Steward | Other Partner(s) | Time Frame | Keyword | Key Initiative Connection
| NS 1.1.1 | Update zoning as guided by the Northgate Future Land Use Map (see Figure 52). | OPCD |  | Medium-term | Zoning
| NS 1.2.1 | Explore the use of incentives or requirements for (a) accessible housing that meets the needs of people with limited mobility, and (b) housing with multiple bedrooms and child-friendly features that meet the needs of families with young children, and (c) residential development that is designed to accommodate multigenerational living. | OPCD |  | Long-term | Zoning
| NS 1.2.2 | Encourage the development of housing types that provide opportunities for homeownership, ranging from lowrise and middle housing units to opportunities for condominium ownership in higher density residential development | OPCD |  | Long-term | Homeownership
| NS 1.2.3 | Support Indigenous-led coalition building for a community land trust development; specifically, one geared toward urban Native communities that would align with the Native Neighborhood vision. Explore the use of public funds or lands to help support this vision becoming a reality. | OPCD |  | Long-term | CLT | Native Neighborhoods
| NS 1.3.1 | Promote the development of new income-restricted housing in Northgate, including through funding, site availability, and other supports | OPCD |  | Long-term | Affordable housing
| NS 1.3.2 | Identify opportunities to acquire and rehabilitate existing affordable market rate residential buildings in Northgate for long-term affordability | OPCD | OH | Long-term | Affordable housing
| NS 1.3.3 | Identify publicly owned sites in the Northgate Regional Center that may be available for income-restricted housing | OPCD | OH | Long-term | Affordable housing
| NS 1.3.4 | Use tools to leverage new market development to include and/or fund affordable housing, such as Multifamily Tax Exemption and Mandatory Housing Affordability | OPCD | OH | Long-term | Affordable housing
| NS 1.3.5 | Explore requiring the production and preservation of income-restricted housing as part of master plans and development agreements | OPCD |  | Long-term | Affordable housing
Neighborhood for All Seasons | NS 1.4.1 | Encourage, and in strategic locations require, new development to incorporate ground-floor commercial uses that contribute to a mix of uses that make it easy to walk to everyday needs such as grocery stores, pharmacies, or tenants that offer arts/culture access. Confirm that the right of way allocation generally prioritizes generous sidewalks, activity zones, trees, and commercial loading over street parking. | OPCD |  | Short-term | Ground floor commercial
Neighborhood for All Seasons | NS 1.4.2 | Consider a pattern of dispersed density by allowing additional height outside of the densest areas in the immediate walkshed of the light rail station, to provide multifamily housing options throughout the neighborhood. | OPCD |  | Medium-term | Zoning
Neighborhood for All Seasons | NS 1.4.3 | At the incoming Seattle Housing Authority redevelopment site, partner with local CBOs and community leaders to identify ground floor uses that provide community benefit. Improve connections between this site and Hubbard Homestead Park, the mall site, and the western portion of the Regional Center. | OPCD | SHA | Short-term | SHA site
Neighborhood for All Seasons | NS 1.4.4 | When sites are redeveloped, require new developments to break up long blocks with pedestrian pathways that over time will seamlessly connect to the wider grid system. | OPCD |  | Short-term | Ped pathways | 8 - Ped Pathways
Neighborhood for All Seasons | NS 2.1.1 | Increase tree planting with trees that are climate-compatible, edible, and/or native, where possible. One priority location includes the park outside the community center and library. The Green Seattle Partnership Program could be a resource, for example. | SPR |  | Short-term | Tree canopy | 7 - Tree Canopy
Neighborhood for All Seasons | NS 2.1.2 | Foster tree canopy expansion on private property and at schools with the Trees for Neighborhoods program, which provides free trees along with guidance for ongoing care and maintenance. | SPR |  | Long-term | Tree canopy | 7 - Tree Canopy
Neighborhood for All Seasons | NS 2.2.1 | Study the potential to install shade structures, prioritizing locations in the public realm, within parks, and along the path from the light rail station to the library. Measure the feasibility of key locations such as the John Lewis Memorial Bridge. | SDOT | SPR | Medium-term | Shade structures
Neighborhood for All Seasons | NS 2.2.2 | Integrate playable water features into the public realm. This could include a splash pad at Hubbard Homestead Park and/or within a new development site. | SPR |  | Medium-term | Water Features | 4 - Hubbard Homestead
Neighborhood for All Seasons | NS 2.2.3 | For new development, encourage green roofs and walls or the use of cool pavement and roof materials. Cool pavement and roof strategies can also be applied to existing sites. | OPCD |  | Short-term | Cooling
Neighborhood for All Seasons | NS 2.3.1 | Work with community-based organizations to identify potential locations and partners for cooling locations. Resource these entities to boost their ability to serve as resilience hubs. | OSE |  | Short-term | Cooling
Neighborhood for All Seasons | NS 2.3.2 | Evaluate providing direct funding for specific needs and/or apply for grants in partnership with the organization to help resource site needs, such as heat pump installation, weatherization, renewable energy systems (such as solar), backup battery energy storage, external and internal shade structures, or supplying organizations with portable air conditioners. | SCL |  | Medium-term | Sustainable buildings
Neighborhood for All Seasons | NS 3.1.1 | Consider expanding the community center to include functions such as a larger fitness area with more equipment, additional multipurpose rooms for classes and meetings, or a swimming pool. | SPR |  | Long-term | Community Center
Neighborhood for All Seasons | NS 3.1.2 | Better integrate the existing library branch with the community center by, for example, creating joint programming opportunities, such as reading hours followed by arts and crafts activities. | SPL |  | Short-term | Library
Neighborhood for All Seasons | NS 3.1.3 | Consider public space incentives within private developments. | OPCD |  | Medium-term | Zoning
Neighborhood for All Seasons | NS 3.2.1 | Create a mid-block pedestrian corridor as a new outdoor public space (Northgate Square), connecting from the light rail out toward neighborhood destinations like the movie theater. | OPCD |  | Medium-term | Mid-Block Corridor | 3 - Northgate Square
Neighborhood for All Seasons | 3.2.2 | Look for opportunities to acquire space for public parks. | SPR |  | Long-term | Open space
Neighborhood for All Seasons | NS 3.2.3 | Add recreation features like outdoor gym equipment, chess boards, cover and lighting for the skate park, and walking paths to motivate adults to use existing parks. Consider the needs of older adults by including equipment designed to increase balance and coordination. | SPR |  | Short-term | Recreation
Neighborhood for All Seasons | NS 3.2.4 | Add more shade structures in parks, especially where mature trees are not planted or are not yet developed. | SPR |  | Medium-term | Shade structures
Neighborhood for All Seasons | NS 3.2.5 | Integrate a splash pad within a local park. | SPR |  | Medium-term | Water Features
Neighborhood for All Seasons | NS 3.2.6 | Find opportunities to accommodate lingering or resting while implementing the ecology corridor and/or food forest concepts. | SPR |  | Medium-term | Cooling
Neighborhood for All Seasons | NS 3.3.1 | Seek to partner with existing or future CBOs to create publicly accessible activations that they can manage. | DON |  | Medium-term | Public Realm
Neighborhood for All Seasons | NS 3.3.2 | Incorporate more fun and playful touches throughout the urban environment with interventions like pocket parks, playful bus stop designs, and public art projects. | OPCD | ARTS | Short-term | Public Realm
Neighborhood for All Seasons | NS 3.3.3 | Look for opportunities to add standards to mid-block corridors that allow the spaces to be more usable for public gathering/lingering, rather than just passages every time. | OPCD |  | Medium-term | Mid-Block Corridor
Neighborhood for All Seasons | NS 3.3.4 | Provide City staff capacity to lead and support programming initiatives, such as special events, particularly near local businesses that can benefit from the additional foot traffic. | OED | DON | Short-term | Events
Neighborhood for All Seasons | NS 3.3.5 | Lean into multifunctional space where possible, with repurposed parking lots, schoolyards open to the public outside of operating hours, and partnership with North Seattle College. | OPCD |  | Short-term | Flexible Space
Living with Place | LP 1.1.1 | Steward natural areas in forested parks and plant more trees in developed parks through the Green Seattle Partnership Program. | SPR |  | Medium-term | Tree canopy
Living with Place | LP 1.1.2 | Foster tree canopy expansion on private property and at schools with the Trees for Neighborhoods program, which provides free trees along with guidance for ongoing care and maintenance. (Note – this action also exists under Policy NS 2.1) | DON |  | Medium-term | Tree canopy
Living with Place | LP 1.1.3 | Update Northgate’s Overlay District to align with Streets Illustrated street type designations and design guidance. Strengthen tree canopy coverage guidelines for new development sites. | OPCD |  | Short-term | Design Guidelines | 7 - Tree Canopy
Living with Place | LP 1.2.1 | Explore the installation of air quality sensors and work with agencies like the State’s Department of Ecology, to monitor air quality in locations around the Regional Center, including sites in close proximity to the freeway. Use this data to identify priority locations for increased tree canopy. | OPCD |  | Short-term | Air Quality | 7 - Tree Canopy
Living with Place | LP 1.2.2 | Identify sites buffering the interstate for increased noise and air quality buffering. In particular, work with the SHA redevelopment site to prioritize plantings and/or visual barriers along its western border. | OPCD | SHA | Medium-term | SHA site
Living with Place | LP 1.2.3 | Explore partnering with SHA for a mass timber pilot project on their redevelopment site. | OPCD | SHA | Long-term | SHA site
Living with Place | LP 1.3.1 | Evaluate restoration opportunities to make the South Branch of Thornton Creek healthier and more accessible to the public. Strategically invest in culvert replacement to seek the best possible improvements for salmon, beaver, and other wildlife through the habitat corridor. | OSE |  | Short-term | Water Quality
Living with Place | LP 1.3.2 | Clear Beaver Pond of invasive species using low impact, integrated pest management methods. Reintroduce native and climate-resilient plant and tree species to Thornton Creek and use enclosures to protect trees and shrubs from resident beaver populations. | SPR |  | Short-term | Beaver Pond | 5 - Ecology Corridor
Living with Place | LP 1.4.1 | Improve the capacity of drainage systems, particularly in identified areas of constraint. | SPU |  | Short-term | Drainage
Living with Place | LP 1.4.2 | Use incentives to promote developer participation in SPU’s Beyond Code Program to exceed stormwater management requirements, protecting Thornton Creek through additional water quality treatment and/or peak flow control. | SPU | OPCD | Short-term | Sustainable buildings
Living with Place | LP 1.5.1 | Complete a performance audit on public facilities in the subarea against resilience hub features and improve the function of places such as the library, community center, incoming fire station, and others to serve as sites of community resilience during extreme weather events. This could include the installation of solar panels on roofs backup generators, and emergency medical supplies (example sites: Kraken Community Iceplex, faith-based buildings). | OSE |  | Short-term | Resilience Hubs
Living with Place | LP 1.5.2 | Consider technical assistance or developer decarbonization incentive utilizing the Seattle Building Emissions Performance Standard regulations and Clean Buildings Accelerator program to exceed City and State emissions and carbon waste requirements. Evaluate if any buildings in Northgate are good candidates for partnership with the Building Emissions Navigator Program. | SDCI | OSE, OPCD | Medium-term | Sustainable buildings
Living with Place | LP 2.1.1 | Establish new park entrances and safe pathways to enhance park accessibility, particularly at Hubbard Homestead and Beaver Pond. | SDOT | SPR | Medium-term | Park access | 4 - Hubbard Homestead
Living with Place | LP 2.1.2 | Partner with King County Metro as they assess east-west bus route reorientation to provide direct access from Northgate to Lake Wahsington (east) and the Puget Sound (west). | SDOT | King County | Long-term | Park access
Living with Place | LP 2.2.1 | Continue to work with North Seattle College to establish a food forest in Barton Woods. Also establish foraging friendly plantings across open spaces in Northgate, aligned with Seattle’s Food Action Plan. | OPCD | North Seattle College | Medium-term | Food forest | Native Neighborhoods
Living with Place | LP 2.2.2 | Integrate community gardens into various sites within and around the Regional Center, such as Hubbard Homestead Park, at the community center, and at local schools. | DON |  | Short-term | Community gardens
Living with Place | LP 2.3.1 | Explore resources necessary to improve amenities at Victory Creek Park. | SPR |  | Medium-term | Victory Creek Park
Living with Place | LP 2.3.2 | Update incentives and explore new strategies for increasing privately owned public spaces as part of new development. | SPR |  | Short-term | Open space
Living with Place | LP 2.3.3 | Identify opportunities for new pocket parks throughout the Regional Center, particularly in areas anticipated to increase their density. | SPR |  | Short-term | Pocket parks
Living with Place | LP 3.1.1 | Develop planting guides for the various conditions across the identified ecology corridor, prioritizing edible, native, and/or climate-resilient species that offer wide canopies. This includes freeway buffer areas, rights-of-way along arterial and neighborhood streets, within Barton Woods, and on redeveloped private property sites. Use the guides found in the Implementation chapter of this report as a starting point. Coordinate with Urban Forestry Core Team for development of each planting guide. | OPCD | OSE, SDOT | Short-term | Ecology corridor | 5 - Ecology Corridor
Living with Place | LP 3.1.2 | Create or adapt existing planting guides for homeowners throughout Northgate for an overall local increase in native, climate-resilient, edible, and pollinator-friendly species in the Regional Center. Raise awareness about resources within Northgate to boost the success of these recommendations. | OPCD | OSE | Short-term | Ecology corridor | 5 - Ecology Corridor
Living with Place | LP 3.1.3 | Partner with resilience hubs sites to connect with homeowners and offer planting guides, free or discounted starter plants, and/or home gardening courses with a focus on selected species in the planting guides. | OSE |  | Short-term | Tree canopy | 7 - Tree Canopy
Living with Place | LP 3.2.1 | Update internal systems to realize the ecology corridor concept, like changing the Green Factor score sheet to allocate additional points for use of preferred species types in this area, creating more space for planting in the ROW, and/or adding setback requirements for private developments. | OPCD |  | Medium-term | Ecology corridor | 5 - Ecology Corridor
Living with Place | LP 3.2.2 | Identify partners at Tribal governments, WSDOT (I-5), North Seattle College (Barton Woods), and among private developers to share planting guides and brainstorm pathways to realizing a cohesive and connected ecology corridor strategy. | OPCD | OSE, SDOT | Medium-term | Ecology corridor | 5 - Ecology Corridor
Living with Place | LP 3.2.3 | Develop interpretive signage along the ecology corridor to share the concept with the public, expand awareness and support for the concept, and educate community members on habitat connectivity benefits and the pre-mall landscape history of Northgate. | SPU | OPCD | Medium-term | Ecology corridor | 5 - Ecology Corridor
Create Northgate | CN 1.1.1 | Use tools such as "Green Street" and "Pedestrian Zone" designations to bring the Northgate Overlay District into alignment with recommendations in the Connected Communities chapter and Future Land Use Map. | OPCD | SDCI | Short-term | Design Guidelines
Create Northgate | CN 1.1.2 | Address sidewalk deficiencies and improve landscaping and buffering, particularly within smaller and moderate scale commercial nodes. | SDOT | SDCI | Long-term | Sidewalk
Create Northgate | CN 1.1.3 | Encourage on-site access for critical access needs (such as garbage collection) as sites redevelop to minimize demands on the curb and sidewalk, where possible. | SDOT | SDCI | Short-term | Curb management
Create Northgate | CN 1.2.1 | Establish a neighborhood brand identity, reflected by elements such as storm drain covers, lamp posts, plantings, murals, and signage. | OPCD | ARTS, SPU, SCL | Short-term | Branding
Create Northgate | CN 1.2.2 | Provide clear and consistent guidance to developers so that new projects contribute to neighborhood identity and an enhanced public realm. | OPCD |  | Short-term | Design Guidelines | 2 - Northgate Way and 5th Ave NE
Create Northgate | CN 1.2.3 | Update and add features to the I-5 underpass so that it is more pedestrian-friendly, safer, and more welcoming. | SDOT | WSDOT | Medium-term | I-5 underpass | 1 - Underpass
Create Northgate | CN 1.2.4 | Partner with King County, Sound Transit, and potential private developers to plan for the Northgate Square concept and realize the intent for the space. Adapt the existing code language to enhance the function of this defined mid-block corridor. | OPCD | King County, Sound Transit | Short-term | Mid-Block Corridor | 3 - Northgate Square
Create Northgate | CN 1.2.5 | Partner with King County and the community to activate the underutilized dropoff/pickup space directly adjacent to the light rail station. | SDOT | Sound Transit, Kraken Iceplex | Short-term
Create Northgate | CN 1.3.1 | Work with Tribal governments, urban Indigenous organizations, Indigenous designers and artists to reflect Native cultures in the public realm. | OPCD | ARTS | Short-term | Public art | Native Neighborhoods
Create Northgate | CN 2.1.1 | Identify locations that are particularly dark for people walking, biking, and driving, and improve lighting conditions, particularly in areas such as the I-5 underpass and corridors with high pedestrian traffic. | SDOT | SCL, WSDOT | Short-term | Lighting | 1 - Underpass
Create Northgate | CN 2.2.1 | Build traffic calming measures into future SDOT projects in the Regional Center. | SDOT |  | Long-term | Traffic Calming
Create Northgate | CN 2.2.2 | Design pedestrian crossings along major roads that are clearly marked and accessible. | SDOT |  | Short-term | Street crossings | 2 - Northgate Way and 5th Ave NE
Create Northgate | CN 2.3.1 | Implement safe routes to school improvements adjacent to at K-12 schools that serve Northgate families, especially at James Baldwin Elementary, Hazel Wolf K-8, and Olympic View Elementary. | SDOT | SPS | Medium-term | SRTS
Create Northgate | CN 2.3.2 | Work with schools to identify barriers for active commuting and find programmatic changes to address these challenges, such as walking or biking school buses, bike donations, or other solutions. | SDOT | SPS | Medium-term | Active Mobility
Create Northgate | CN 2.4.1 | Train EMTs, firefighters, and police officers who serve Northgate’s community in de-escalation techniques, mental health first aid, and compassionate response approaches when working with individuals experiencing homelessness, such as connecting people to service providers and care networks. | SFD |  | Short-term | First responders
Create Northgate | CN 3.1.1 | Leverage the new fire station being built along Meridian as an opportunity to add art and color to the public realm. | SFD |  | Short-term | Fire station
Create Northgate | CN 3.1.2 | Identify additional opportunities with public facilities and public property in Northgate to integrate art and color in new ways. | OPCD | ARTS | Long-term | Public Art
Create Northgate | CN 3.2.1 | Identify partners to implement public art at the intersection of Northgate Way and 5th Avenue. | ARTS |  | Medium-term | Public Art | 2 - Northgate Way and 5th Ave NE
Create Northgate | CN 3.2.2 | Integrate art, along with lighting and safety buffering, at the I-5 underpass. | SDOT | ARTS, WSDOT | Medium-term | I-5 underpass | 1 - Underpass
Connected Communities | CC 1.1.1 | Continually assess and improve walking, biking, and transit access conditions in the immediate transit station area. Make investments as necessary to better connect people using these modes to the station, particularly within walking distance of the station. | SDOT |  | Medium-term | Transit station area
Connected Communities | CC 1.1.2 | Fill in gap areas for safe, on-site parking for bicycles, including larger cargo and family-size bikes, and scooters in the transit station and at community destinations. | SDOT | SDCI, Sound Transit | Short-term | Bike facilities
Connected Communities | CC 1.1.3 | Add more wayfinding and create a consistent wayfinding look and feel between community destinations and the station. | SDOT |  | Medium-term | Wayfinding
Connected Communities | CC 1.1.4 | Continue to work with major employers, such as the University of Washington Medical Center, not within short walking distance of the light rail station to improve access to the station and other transit and shift commuters away from single occupancy vehicle commutes. | SDOT | King County Metro | Medium-term
Connected Communities | CC 1.2.1 | Leverage emerging mobility technology, such as on-demand “microtransit” buses or shuttles and shared ebikes and scooters, to provide first-/last-mile service to the light rail station and other Community & Mobility Hubs. | SDOT |  | Short-term | Micromobilitly
Connected Communities | CC 1.2.2 | Co-create Community & Mobility Hubs within Northgate at locations indicated in the STP to enhance the waiting and transfer experience for transit riders. | SDOT |  | Medium-term | Mobility hubs
Connected Communities | CC 1.2.3 | Work with Northwest Hospital to provide subsidized e-bike and scooter service to employees. | SDOT |  | Medium-term | Micromobilitly
Connected Communities | CC 1.2.4 | Use bus shelters as opportunities to integrate public art and reflect an enhanced identity for Northgate. | SDOT | King County Metro | Short-term | Bus shelters
Connected Communities | CC 1.2.5 | Complete the Transit Network outlined in the STP. | SDOT |  | Long-term | Transit improvements
Connected Communities | CC 1.2.6 | Work with King County Metro to prioritize off-street layover space either at their existing site - incorporated into a transit-oriented development - or in a new location nearby. | King County Metro |  | Medium-term
| CC 2.1.1 | Make the Northgate Way underpass more pleasant for people walking through interventions such as adding art, improving lighting, enhancing crossings on either side of the underpass, and potentially reconfiguring the street to widen the sidewalk and/or add a buffer. | SDOT |  | Medium-term | I-5 crossings
| CC 2.1.2 | Study the potential to install shade structures or other weather-proofing measures on the John Lewis Memorial Bridge. | SDOT |  | Medium-term | I-5 crossings
| CC 2.1.3 | Better connect the UW Medical Campus to the rest of the Regional Center by adding bike facilities for people of all ages and abilities to Meridian Ave N. | SDOT |  | Medium-term | I-5 crossings
| CC 2.1.4 | Widen the sidewalk on 1st Ave NE over I-5 to better serve people walking, rolling, and biking over the highway. | SDOT |  | Medium-term | I-5 crossings
| CC 2.1.5 | Evaluate 92nd St NE for ways to make walking, rolling, and biking more comfortable | SDOT |  | Medium-term | I-5 crossings
Connected Communities | CC 2.2.1 | Fill in sidewalk gaps connecting the Regional Center to surrounding neighborhoods and deficiencies or declining conditions on sidewalks within Northgate. | SDOT |  | Long-term | Sidewalk
Connected Communities | CC 2.2.2 | Using The Northgate Potential Block Pattern Map as a guide (Figure 45), require that future development contributes to enhanced connectivity in Northgate. | SDOT | OPCD, SDCI | Short-term | Ped pathways | 8 - Ped Pathways
Connected Communities | CC 2.2.3 | Update the Northgate Overlay District to identify locations where new public and private streets and pedestrian or cycling pathways will be built as land redevelops. | OPCD |  | Short-term | Design Guidelines | 8 - Ped Pathways
Connected Communities | CC 2.2.4 | Require that major planned sites have a coordinated plan for connectivity. | SDOT | SDCI | Short-term | Design Guidelines | 8 - Ped Pathways
Connected Communities | CC 2.2.5 | Identify retroactive solutions on existing sites with desired paths, such as 3rd Ave NE between NE 97th and NE 95th or between multifamily buildings adjacent to, but disconnected from, the library and community center. | SDOT | SDCI | Short-term | Ped pathways | 8 - Ped Pathways
Connected Communities | CC 2.3.1 | Complete the Pedestrian and Bicycle and E-Mobility Networks outlined in the STP. | SDOT |  | Short-term | Ped/Bike Networks | 2 - Northgate Way and 5th Ave NE
Connected Communities | CC 2.3.2 | Extend the multiuse trail that currently dead ends at the light rail station coming from the south. Continue the pathway north to 115th, where it can link with the I-5 crossing. | SDOT |  | Long-term | Multiuse trail | 6 - Major Transportation Improvements
Connected Communities | CC 2.3.3 | Among other modal priorities, create “all ages and abilities” biking corridors on Meridian Ave and 5th Ave NE. | SDOT |  | Medium-term | Bike facilities | 6 - Major Transportation Improvements
Connected Communities | CC 2.4.1 | Integrate the strategies outlined in SDOT’s Vision Zero Action Plan in street redesigns as the pedestrian, bicycle, e-mobility, and transit networks are built out. | SDOT |  | Short-term | Vision Zero | 2 - Northgate Way and 5th Ave NE
Connected Communities | CC 2.4.2 | In coordination with WSDOT, improve the experience and safety of three I-5 crossings in and around the Northgate Regional Center—Northgate Way, 1st Avenue NE, and NE 92nd Street— for all travelers, but especially the most vulnerable (i.e., people walking, biking, and rolling). | SDOT | WSDOT | Medium-term | I-5 crossings | 1 - Underpass
Connected Communities | CC 2.4.3 | Add and enhance existing crosswalks along key corridors, such as NE Northgate Way, 5th Avenue, and Meridian Ave. | SDOT |  | Long-term | Street crossings | 2 - Northgate Way and 5th Ave NE
Connected Communities | CC 2.4.4 | Improve the connective experience for those biking, rolling, or walking from Aurora to the west across the John Lewis Memorial Bridge. | SDOT |  | Medium-term | Bike facilities
Connected Communities | CC 2.5.1 | Conduct a parking study for the Regional Center to right size the supply of on-street and surface parking spaces. | SDOT |  | Medium-term | Parking
Connected Communities | CC 2.5.2 | Revise the development code to establish a parking maximum, reduce the overall supply of parking, and encourage more efficient use of existing parking. | SDOT | OPCD, SDCI | Short-term | Curb management
Connected Communities | CC 2.5.3 | Revise the development code to encourage that critical access needs (such as garbage collection and loading/unloading) be met on site as redevelopment occurs to minimize conflicts on the curb and sidewalk, where possible. | SDOT | OPCD, SDCI | Short-term | Curb management
Connected Communities | CC 3.1.1 | Partner with community members to co-create a PSPS Plan for Northgate, building on the Regional Center Plan, which will identify which types of People Streets and Public Spaces people want to see in the neighborhood and where. | SDOT |  | Medium-term | PSPS
Connected Communities | CC 3.1.2 | Cultivate community gathering spaces that encourage lingering at or near the Northgate light rail station and the other Community & Mobility Hubs planned in Northgate, as indicated in the STP. Different types of amenities and placemaking features can exist at these hubs, and it will be important for the community to weigh in on what these will look like. | SDOT | King County Metro | Medium-term | Mobility hubs
Connected Communities | CC 3.1.3 | Create a mid-block pedestrian corridor (Northgate Square) connecting from the transit station over to 3rd Avenue as part of a cohesive strategy to transform the public realm adjacent to light rail. | SDOT |  | Medium-term | Mid-Block Corridor | 3 - Northgate Square
Connected Communities | CC 3.1.4 | Incorporate edible, native, and/or climate-resilient plantings into the design of landscaping plans for public rights-of-way, in collaboration with the ecology corridor project detailed in Living with Place. This includes using rights-of-way as part of the overall strategy to increase Northgate’s tree canopy coverage. | SDOT |  | Short-term | ROW Plantings | 5 - Ecology Corridor
Connected Communities | CC 3.1.5 | Collaborate with business owners in locally serving commercial nodes when designing streetscape enhancements to maximize benefits for small businesses, address key concerns, and cohesively cultivate a sense of place for the surrounding community. | OPCD |  | Short-term | Public realm
Connected Communities | CC 3.2.1 | Improve pedestrian access to Hubbard Homestead Park. | SDOT |  | Short-term | Park access | 4 - Hubbard Homestead
Connected Communities | CC 3.2.2 | Use context-sensitive design practices for all future transportation facility projects. | SDOT |  | Long-term | Facility design
Shared Abundance | SA 1.1.1 | Improve the access infrastructure, streetscapes, and event programming along the locally serving commercial corridors for an enhanced visitor experience. | OPCD |  | Short-term | Commercial Corridors
Shared Abundance | SA 1.1.2 | Build and maintain connections between qualifying businesses, non-profits, and the City’s Equitable Development Initiative. | OED |  | Medium-term | Small Business Funds
Shared Abundance | SA 1.2.1 | Connect small business owners to City programs such as the Small Business Capital Access Program, Tenant Improvement Funds, or Business Community Ownership Fund, among others. | OED |  | Short-term | Small Business Funds
Shared Abundance | SA 1.2.2 | Explore the creation of “commercial preservation zones” that aim to maintain commercial culture and character of clusters of small and BIPOC-owned businesses. | OPCD |  | Long-term | Commercial Corridors
Shared Abundance | SA 1.2.3 | Partner with existing non-profits such as Ventures to support small businesses through technical assistance and training, commercial leasing, and access to capital. This program can also assist small businesses to be placed in larger commercial developments. | OED |  | Short-term | Technical assistance
Shared Abundance | SA 1.2.4 | Aim to leverage public land ownership adjacent to the station area for the integration of income-restricted affordable housing, land trust housing cooperatives, or ownership housing opportunities. | OH |  | Medium-term | Affordable housing
Shared Abundance | SA 1.2.5 | Offer targeted tenant relocation funds for development sites where existing housing will be removed so residents can remain in the community if they desire. When possible, connect these residents with opportunities for incoming income-restricted units. | OH |  | Short-term | Tenant relocation funds
Shared Abundance | SA 1.2.6 | Partner with business owners during construction projects in the right of way that impact visitor access to their establishments and mitigate these impacts. | OED |  | Medium-term
Shared Abundance | SA 2.1.1 | Increase allowed density in throughout the Center for a resident base that can support a wider range of businesses. Maintain or add ground floor commercial requirements in select focused areas for locally serving commercial nodes. | OPCD |  | Short-term | Zoning
Shared Abundance | SA 2.1.2 | Explore opportunities within the land use code to require or encourage smaller and more flexible commercial spaces that can be affordable to start up businesses. Work to connect property owners with interested entrepreneurs to enhance the success of these spaces. | OPCD |  | Short-term | Ground floor commercial
Shared Abundance | SA 2.2.1 | Explore commercial affordability programs or incentives for new development to build out more of their commercial space to lower tenant improvement costs. | OED |  | Medium-term | Commercial Affordability
Shared Abundance | SA 2.2.2 | Identify vacant retail spaces for businesses to enter and match with businesses looking to expand. | OED |  | Medium-term | Business Collaboration
Shared Abundance | SA 2.2.3 | Use empty parking lots in convenient locations, such as adjacent to light rail, for pop-up markets and food trucks. | DON |  | Short-term | Flexible space
Shared Abundance | SA 2.2.4 | Decrease the footprint of surface parking through land use policy in Northgate, particularly in the high-density core. | OPCD |  | Medium-term | Zoning
Shared Abundance | SA 2.3.1 | Explore additional partnerships with North Seattle College, the University of Washington Medical Center - Northwest, and other private and public agencies to enhance resident opportunities for accessing career pathways with stronger prospects for middle-wage jobs. Identify opportunities from the City’s Key Industries Workforce Development program. | OED |  | Medium-term | Workforce development
Shared Abundance | SA 2.3.2 | Leverage larger sites and parcels in this Regional Center for unique uses in the entertainment and recreation sectors for a healthy clustering of activity. | Private Sector |  | Medium-term | Development
Shared Abundance | SA 3.1.1 | Partner with Indigenous leaders to identify suitable locations in Northgate for the siting of an Indigenous Opportunity Center. | OED | OPCD | Short-term | Indigenous Opportunity Center | Native Neighborhoods
Shared Abundance | SA 3.1.2 | Pair incoming development sites with businesses and nonprofits that meet existing community needs and reflect neighborhood diversity. | OED | SDCI | Medium-term | Development
Shared Abundance | SA 3.2.1 | Host stakeholder meetings among 1) existing businesses and services and 2) developers of key sites in the neighborhood to explore areas for cooperation and collective benefit. Share information about available resources and services from existing City programs. | OED |  | Short-term | Business Collaboration
Shared Abundance | SA 3.2.2 | Conduct outreach with leaders in the business community to determine interest at the local level for a neighborhood business association or similar entity. | OED |  | Long-term | Business Support
| SA 3.3.1 | Identify boundary options for potential expansion based on existing and potential future land uses and activities and connectivity to transit and areas with the current Regional Center boundary | OPCD |  | Short-term | Boundary
| SA 3.3.2 | Continue outreach and collaboration with North Seattle College and stakeholders in the surrounding community about potential inclusion in the Regional Center | OPCD |  | Short-term | Boundary
| SA 3.3.3 | Coordinate any proposal for boundary change with regional partners including the Puget Sound Regional Council and the Growth Management Planning Council | OPCD |  | Short-term | Boundary

## SDOT Project List
Project | Project ID | Project Title | Extents | Project Description (External) | STP Project ID | Project Type | Level of Effort (Low/Medium/High) | Community Priority from Fall 2024 Survey?
1 | 1 | UWMC-Northwest Bike+ Connection | N 115th St (UMNW Campus entrance to Meridian Ave N) | Add "all ages and abilities" bicycle facilities on N 115th St that connect to UW Medical Center NW. |  | Bike | Low
2 | 2 | 1st Ave NE Overpass to N Northgate Way Bike+ Connection | Meridian Ave N (N Northgate Way to N115th St); N 115th St (Meridian Ave N to Corliss Ave N); Corliss Ave N (N 115th St to N 117th St); N 117th St (Corliss Ave N to 1st Ave NE) | Create an "all ages and abilities" bike connection west of I-5 and north of N Northgate way that connects existing bike facilities on Meridian Ave with the 1st Ave NE overpass and James Baldwin Elementary School. |  | Bike | Low
3 | 3 | Corliss Ave N Pedestrian Improvements | Corliss Ave N (N 113th St to N 107th St) | Add continuous sidewalks and street trees as well as a new pedestrian connection along Corliss Ave N. This will provide an additional north-south route for people walking and rolling west of I-5 within Northgate. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | High
3 | 3.1 | Corliss Ave N Pedestrian Improvements - New Sidewalks North | Corliss Ave N (N 113th St to N Northgate Way) | Add continuous sidewalks and street trees along Corliss Ave N to safely connect people walking and rolling to services on Northgate Way. Study feasibility of a new pedestrian connection on Corliss Ave N at N 112th St where Corliss Ave N currently deadends. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | High
3 | 3.2 | Corliss Ave N Pedestrian Improvements - New Sidewalks South | Corliss Ave N (N Northgate Way to N 107th St) | Add continuous sidewalks and street trees along Corliss Ave N to safely connect people walking and rolling to services on Northgate Way. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | High
3 | 3.3 | Corliss Ave N Pedestrian Improvements - New Crossing | Corliss Ave N at N 107th St | Pending addition of sidewalks to Corliss Ave N, add a new crossing across N 107th St to safely connect people walking and rolling to services on Northgate Way. This project has multiple line items. See all line items for full scope of project. |  | Crossing | Low
4 | 4 | Northgate Way & I-5 Underpass Multimodal Improvements | Northgate Way (Meridian Ave N to 5th Ave NE) | Make improvements along Northgate Way and the I-5 underpass to improve pedestrian safety and support transit and freight. This project has multiple line items. See all line items for full scope of project. | 26 | Corridor | High | Yes
4 | 4.1 | Northgate Way & I-5 Underpass Multimodal Improvements - Community & Mobility Hub at Meridian Ave N | N Northgate Way & Meridian Ave N | Study and implement a Community & Mobility Hub. This project has multiple line items. See all line items for full scope of project. | 26 | Community & Mobility Hub | Medium
4 | 4.2 | Northgate Way & I-5 Underpass Multimodal Improvements - Pedestrian Safety Improvements at Corliss Ave N | N Northgate Way & Corliss Ave N | Make pedestrian safety improvements at the intersection of N Northgate Way & Corliss Ave N, including potential reconfiguration of I-5 On/Off ramps. This project has multiple line items. See all line items for full scope of project. | 26 | Intersection Redesign | Medium | Yes
4 | 4.3 | Northgate Way & I-5 Underpass Multimodal Improvements - Corridor Improvements | Northgate Way (Meridian Ave N to 5th Ave NE) | Make pedestrian safety and experience improvements as well transit supportive improvements along Northgate Way, paying particular attention to the I-5 underpass. This project has multiple line items. See all line items for full scope of project. | 26 | Corridor | Medium | Yes
4 | 4.4 | Northgate Way & I-5 Underpass Multimodal Improvements - Pedestrian Safety Improvements at 1st Ave NE | NE Northgate Way & 1st Ave N | Make pedestrian safety improvements at the intersection of NE Northgate Way & 1st Ave NE, including a connection to the future multi-use trail along 1st Ave NE and a potential reconfiguration of the I-5 On/Off Ramps. This project has multiple line items. See all line items for full scope of project. | 26 | Intersection Redesign | Medium | Yes
4 | 4.5 | Northgate Way & I-5 Underpass Multimodal Improvements - Crossing improvements at 3rd Ave NE | NE Northgate Way & 3rd Ave NE | Improve the crossing experience across Northgate Way at 3rd Ave NE near Target. Potential improvements to evaluate include: -Adding east leg of crosswalk -Retiming the signal to extend the amount of time people have to cross This project has multiple line items. See all line items for full scope of project. | 26 | Crossing | Medium | Yes
4 | 4.6 | Northgate Way & I-5 Underpass Multimodal Improvements - Midblock Crossing | NE Northgate Way between 3rd Ave NE and 5th Ave NE | Study feasibility of a midblock crossing across Northgate Way at the existing pedestrian path between Target & Best Buy. People currently jaywalk at this location frequently. This project has multiple line items. See all line items for full scope of project. | 26 | Crossing | Medium | Yes
5 | 5 | N Northgate Way Multimodal Improvements | N Northgate Way (Ashworth Ave N to Meridian Ave N) | Redesign the western segment of Northgate Way to support transit, freight, and pedestrian safety. These improvements could include traffic calming, new crosswalks, and sidewalk widening along this High Injury Network corridor. This project has multiple line items. See all line items for full scope of project. | 26 | Corridor | Medium | Yes
5 | 5.1 | N Northgate Way Multimodal Improvements - New Crossing at Ashworth Ave N | N Northgate Way at Ashworth Ave N | Add a new crossing across Northgate Way at Ashworth Ave N, which is identified as "Tier 1" in the STP Enhanced Street Crossings Priority Investment Network. This project has multiple line items. See all line items for full scope of project. | 26 | Crossing | Low | Yes
5 | 5.2 | N Northgate Way Multimodal Improvements - Corridor Improvements | N Northgate Way (Ashworth Ave N to Meridian Ave N) | Evaluate and implement safety improvements along this segment of Northgate Way, which could include repurposing travel lanes, revisions to traffic controls, traffic calming treatments, and/or widening sidewalks on this High Injury Network corridor. This project has multiple line items. See all line items for full scope of project. | 26 | Corridor | Medium | Yes
5 | 5.3 | N Northgate Way Multimodal Improvements - New Crossing at N 107th St | N Northgate Way at N 107th St | Add a new crossing across Northgate Way at N 107th St, which is the entrance to Mineral Springs Park. This location is identified as "Tier 1" in the STP Enhanced Street Crossings Priority Investment Network. This project has multiple line items. See all line items for full scope of project. | 26 | Crossing | Low | Yes
6 | 6 | Meridian Ave N Multimodal Improvements | Meridian Ave N (NE 92nd St to N Northgate Way) | Change the street to support people walking, rolling, and taking transit to North Seattle College, medical facilities, and other services along the corridor. This could include upgrading existing protected bike lanes by adding a vertical barrier and adding or upgrading crosswalks. This project has multiple line items. See all line items for full scope of project. |  | Corridor | Medium | Yes
6 | 6.1 | Meridian Ave N Multimodal Improvements - Better Bike Barriers | Meridian Ave N (NE 92nd St to N Northgate Way) | Upgrade existing protected bike lanes on Meridian Ave N and College Way N to add a vertical barrier, such as a concrete curb, to address people parking their vehicles in the bike lanes and community-identified safety concerns. This project has multiple line items. See all line items for full scope of project. |  | Bike | Medium | Yes
6 | 6.2 | Meridian Ave N Multimodal Improvements - Signal/AWS Designations | Meridian Ave N (N Northgate Way to N 103rd St) | Explore converting the whole corridor to a consistent crossing type - either only All Way Stops or only Signals to provide a more consistent crossing experience. This project has multiple line items. See all line items for full scope of project. |  | Traffic Ops | Medium | Yes
6 | 6.3 | Meridian Ave N Multimodal Improvements - New Crossing at N 107th St | Meridian Ave N at N 107th St | Add a new crossing across Meridian Ave N at N 107th Street to connect people to residences and medical services. This is identified as "Tier 1" in the STP Enhanced Street Crossings Priority Investment Network. This project has multiple line items. See all line items for full scope of project. |  | Crossing | Low | Yes
6 | 6.4 | Meridian Ave N Multimodal Improvements - New Crossing at N 106th St | Meridian Ave N at N 106th St | Add a new crossing across Meridian Ave N at this King County public health clinic. This project has multiple line items. See all line items for full scope of project. |  | Crossing | Low | Yes
7 | 7 | N 105th and N 107th St Traffic Calming | N 105th St (N Northgate Way to Meridian Ave N); N 107th St (N Northgate Way to Corliss Ave N) | Evaluate and implement traffic calming measures to limit speeding and address cut through traffic on these neighborhood streets. This project has multiple line items. See all line items for full scope of project. |  | Traffic Calming/VZ | Low
7 | 7.1 | N 105th and N 107th St Traffic Calming - N 107th St | N 107th St (N Northgate Way to Corliss Ave N) | Evaluate and implement traffic calming measures to limit speeding and address cut through traffic by people heading to the highway on this neighborhood street. This project has multiple line items. See all line items for full scope of project. |  | Traffic Calming/VZ | Low
7 | 7.2 | N 105th and N 107th St Traffic Calming - N 105th St | N 105th St (N Northgate Way to Meridian Ave N) | Evaluate and implement traffic calming measures to limit speeding and address cut through traffic by people heading to the highway on this neighborhood street. This project has multiple line items. See all line items for full scope of project. |  | Traffic Calming/VZ | Low
8 | 8 | N 107th St, Bagley Ave N, & N 106th St Sidewalk Improvements | N 107th St (Meridian Ave N to Corliss Ave N); Bagley Ave N ( N 107th St to N 106th St); N 106th St (Meridian Ave N to Dead end) | Add or upgrade sub-standard sidewalks and add street trees on these neighborhood streets. |  | Sidewalk | Low
8 | 8.1 | N 107th St, Bagley Ave N, & N 106th St Sidewalk Improvements - N 107th St | N 107th St (Corliss Ave N to Meridian Ave N) | Add sidewalks and street trees on N 107th St |  | Sidewalk | Medium
8 | 8.2 | N 107th St, Bagley Ave N, & N 106th St Sidewalk Improvements - Bagley Ave N | Bagley Ave N ( N 107th St to N 106th St) | Upgrade sub-standard sidewalks on Bagley Ave N |  | Sidewalk | Medium
8 | 8.3 | N 107th St, Bagley Ave N, & N 106th St Sidewalk Improvements - N 106th St | N 106th St (Meridian Ave N to Dead end) | Upgrade sub-standard sidewalks on N 106th St |  | Sidewalk | Medium
9 | 9 | SB I-5 Onramp at N 107th St/Corliss Ave N Improvements | SB I-5 On-ramp at N 107th St/Corliss Ave N | Coordinate with WSDOT to improve merge condition and sightlines on this on-ramp. |  | Vehicle | Medium
10 | 10 | N 100th St Multimodal Improvements | N 100th St (Aurora Avenue to John Lewis Memorial Pedestrian Bridge) | Upgrade sub-standard sidewalks, add pedestrian lighting, and make Neighborhood Greenway enhancements on this connection between Aurora Ave N and John Lewis Memorial Bridge |  | Neighborhood Greenway | Medium
11 | 11 | 1st Ave NE Bridge Multimodal Improvements | 1st Ave NE (N 115th St to NE 117th St) | Widen the facility provided on 1st Ave NE for people who bike, walk, or roll over I-5, reconnecting the Northgate neighborhood. |  | Trail | High
12 | 12 | Hazel Wolf Safe Route to School Improvements | NE 117th St (5th Ave NE to Roosevelt Ave NE); 12th Ave NE (NE 115th St to NE 117th St); NE 115th St at Pinehurst Ave NE | Add sidewalks and redesign intersections to support Safe Routes to School. This project has multiple line items. See all line items for full scope of project. |  | SRTS | Medium
12 | 12.1 | Hazel Wolf Safe Route to School - NE 117th St Sidewalks | NE 117th St (5th Ave NE to Roosevelt Ave NE) | Add sidewalks to improve safety of people walking and rolling to Hazel Wolf Elementary School. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | Medium
12 | 12.2 | Hazel Wolf Safe Route to School - NE 115th St & Pinehurst Ave NE Intersection Improvements | NE 115th St at Pinehurst Ave NE | Redesign the intersection of NE 115th St and Pinehurst Ave NE to create safer crossings for people walking and rolling to Hazel Wolf Elementary School. This project has multiple line items. See all line items for full scope of project. |  | Intersection Redesign | Medium
13 | 13 | 1st Ave NE Bike + Connection | 1st Ave NE (Northgate Station to NE 115th St) | Redesign the street to extend the all ages and abilities bike connection from the Northgate Transit Station to NE 115th St and support transit. | 1 | Corridor | High | Yes
14 | 14 | Hubbard Homestead Park & NE 112th St Midblock Pedestrian crossing | NE 112th St between 3rd Ave NE & 5th Ave NE | Study the feasibility of a new pedestrian crossing that would connect Hubbard Homestead Park to Target and Best Buy midblock on NE 112th St. |  | Crossing | Medium
15 | 15 | 5th Ave NE Multimodal Improvements - North | 5th Ave NE (NE 115th St to NE Northgate Way) | Add “all ages and abilities” bike facilities and upgrade sub-standard sidewalks, improving safety for people who bike, walk, and roll to Hubbard Homestead Park or services along 5th Ave NE |  | Corridor | Medium
16 | 16 | 8th Ave NE Sidewalk Upgrades | 8th Ave NE (NE Northgate Way to NE 115th St) | Upgrade sub-standard sidewalks, improving comfort for people walking or rolling to services along 8th Ave NE and NE Northgate Way. |  | Sidewalk | Medium
17 | 17 | Roosevelt Way NE Multimodal Improvements | Roosevelt Way NE (NE 114th St to NE 108th St) | Redesign the street to support transit and freight movement and upgrade sub-standard sidewalks, improving comfort for people walking or rolling to services on Roosevelt Way NE. | 9 | Corridor | Medium
18 | 18 | NE Northgate Way Multimodal Improvements | NE Northgate way (5th Ave NE to 11th Ave NE) | Redesign the street to improve pedestrian safety and comfort and support freight along NE Northgate Way, including intersection improvements at 5th Ave NE. This project has multiple line items. See all line items for full scope of project. | 56 | Corridor | Medium | Yes
18 | 18.1 | NE Northgate Way Multimodal Improvements- Community & Mobility Hub at 5th Ave NE | NE Northgate Way & 5th Ave NE | Study and implement a Community & Mobility Hub. This project has multiple line items. See all line items for full scope of project. | 56 | Community & Mobility Hub | Medium
18 | 18.2 | NE Northgate Way Multimodal Improvements - 5th Ave NE Signal Improvements |  | Examine and implement improvements to improve pedestrian safety and comfort. This project has multiple line items. See all line items for full scope of project. | 56 | Traffic Ops | Low | Yes
18 | 18.3 | NE Northgate Way Multimodal Improvements - Pedestrian Improvements | 5th Ave Ave NE to 11th Ave NE | Implement treatments that will enhance the pedestrian experience along the commercial portion of NE Northgate Way. This project has multiple line items. See all line items for full scope of project. | 56 | Corridor | Medium | Yes
18 | 18.4 | NE Northgate Way Multimodal Improvements -Roosevelt Ave NE Intersection Redesign | NE Northgate Way & Roosevelt Ave NE | Redesign the intersection to provide protected bike crossings. This project has multiple line items. See all line items for full scope of project. | 56 | Intersection Redesign | Medium | Yes
18 | 18.5 | NE Northgate Way Multimodal Improvements - Community & Mobility Hub at Roosevelt Ave NE | NE Northgate Way & Roosevelt Ave NE | Study and implement a Community & Mobility Hub. This project has multiple line items. See all line items for full scope of project. | 56 | Community & Mobility Hub | Medium | Yes
19 | 19 | 11th Ave NE/ NE 108th St Sidewalks | 11th Ave NE/ NE 108th St (Roosevelt Ave NE to N Northgate Way) | Add sidewalks for people walking and rolling on this neighborhood street |  | Sidewalk | Medium
20 | 20 | 5th Ave NE Multimodal Improvements (South) | 5th Ave NE (NE Northgate Way to NE 95th St) | Redesign 5th Ave NE to support transit, freight, bike, and pedestrian safety. Add new crosswalks, transit improvements, and “all ages and abilities” bike facilities to improve access to the Northgate Library & Community Center, Kraken Community Ice Plex, and other services along 5th Ave NE. This project has multiple line items. See all line items for full scope of project. | 56 | Corridor | Medium | Yes
20 | 20.1 | 5th Ave NE Multimodal Improvements (South) - Corridor improvements | 5th Ave NE (NE Northgate Way to NE 95th St) | Add an all ages and abilities bike connection, upgraded sidewalks, and transit supportive improvements. (Transit improvements would only be from NE Northgate Way to NE 103rd St.) This project has multiple line items. See all line items for full scope of project. | 56 | Corridor | Medium
20 | 20.2 | 5th Ave NE Multimodal Improvements (South) - New Crossing at Entrance to Kraken Community Iceplex | 5th Ave NE & driveway between NE Northgate Way and NE 106th St | Add a new crossing at the driveway entrance to the Kraken Community Iceplex. People frequently jaywalk at this location. This project has multiple line items. See all line items for full scope of project. | 56 | Crossing | Low
20 | 20.3 | 5th Ave NE Multimodal Improvements (South) -New Crossing at NE 105th St | 5th Ave NE & NE 105th Ave | Add a new crossing at NE 105th St, connecting to a future east/west pedestrian path on the Mall redevelopment site. This project has multiple line items. See all line items for full scope of project. | 56 | Crossing | Low
20 | 20.4 | 5th Ave NE Multimodal Improvements (South) -New Crossing at NE 102nd St | 5th Ave NE & NE 102nd St | Add a new crossing at NE 102nd St, connecting people to the Thornton Creek boardwalk. This project has multiple line items. See all line items for full scope of project. | 56 | Crossing | Low
20 | 20.5 | 5th Ave NE Multimodal Improvements (South) - Signal modifications | 5th Ave NE & NE 100th St | Add a northbound left turn lane, no right-on-red signage, and associated signal timing. This project has multiple line items. See all line items for full scope of project. | 56 | Traffic Ops | Low
21 | 21 | NE 105th St Multimodal Improvements | NE 105th St (5th Ave NE to 8th Ave NE) | Examine limiting who can drive on this narrow street to make walking, rolling, and biking on this block more comfortable. It will be an important connection into the Northgate Mall redevelopment via a future pedestrian connection west of 5th Ave NE at NE 105th St. |  | PSPS | Medium
22 | 22 | Neighborhood Sidewalks & Walkways to Light Rail Station | NE 105th St (8th Ave NE to Roosevelt Way NE); NE 103rd St (5th Ave NE to Roosevelt Way NE); NE 100th St (5th Ave NE to Roosevelt Way NE) | Add sidewalks or alternative walkways and street trees to these east/west neighborhood streets to better connect people walking and rolling from neighborhoods to services within Northgate, including the light rail station. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | Medium
22 | 22.1 | New Sidewalks & Walkways - NE 105th St | NE 105th St (8th Ave NE to Roosevelt Way NE) | Add a sidewalk or alternative walkway and street trees on NE 105th St, better connecting people walking and rolling from neighborhoods to Thornton Creek and the Northgate Mall redevelopment. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | Medium | Yes
22 | 22.2 | New Sidewalks & Walkways - NE 103rd St | NE 103rd St (5th Ave NE to Roosevelt Way NE) | Add a sidewalk or alternative walkway and street trees on NE 103rd St, better connecting people walking and rolling from neighborhoods to the Northgate Transit Station. Modify street design to increase compliance with one-way street. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | Medium | Yes
22 | 22.3 | New Sidewalks & Walkways - NE 100th St | NE 100th St (5th Ave NE to Roosevelt Way NE) | Add a sidewalk or alternative walkway and street trees on NE 105th St, better connecting people walking and rolling from neighborhoods to Thornton Creek and the Northgate Transit Station. This project has multiple line items. See all line items for full scope of project. |  | Sidewalk | Medium | Yes
23 | 23 | 8th Ave NE - Multimodal Improvements | 8th Ave NE (NE Northgate Way to NE 95th St) | Provide a variety of improvements to enhance 8th Ave NE as a north/south walking, rolling, and biking corridor. Upgrade the existing Neighborhood Greenway; add either sidewalks or alternative walkways where sidewalks are missing; explore street diversions at 104th or 103rd to minimize cut through traffic; and "daylight" driveways between NE Northgate Way and NE 105th St to improve visibility and safety. |  | Neighborhood Greenway | Medium
24 | 24 | NE 103rd St/ NE 100th St Multimodal Improvements | NE 103rd St (1st Ave NE to 5th Ave NE); NE 100th St (1st Ave NE to 5th Ave NE | Redesign theses streets for people biking and taking transit to the Northgate Transit Station. This will include adding an all ages and abilities bike facility to either NE 103rd St or NE 100th St. |  | Corridor | Low
25 | 25 | 3rd Ave NE Raised Crosswalk | 3rd Ave NE at Thornton Place | Add a raised crosswalk to connect people walking and rolling between the Thornton Place shops and Northgate Transit Station via the future midblock pathway. It would also help calm traffic on 3rd Ave NE. |  | Crossing | Medium
26 | 26 | Community & Mobility Hub at Northgate Station | Northgate Transit Station | Enhance the existing Community & Mobility Hub at the Northgate Station to improve the experience transferring between modes of travel and create a sense of place. This could include working with King County and Sound Transit to host community-driven events on their properties adjacent to the station. |  | Community & Mobility Hub | Medium
27 | 27 | 1st Ave NE Corridor Improvements | 1st Ave NE (92nd St NE to 103rd St NE) | Improve the street for people walking, biking and taking transit to the Northgate Transit Station and services along 1st Ave NE. This could include evaluating speeds and adding traffic calming treatments, making transit improvements where necessary, and adding trail curb cuts to access The Polyclinic and other services on the east side of 1st Ave NE. |  | Corridor | Low
28 | 28 | New Pedestrian Connection - NE 94th St (1st Ave NE -5th Ave NE) |  | Study feasibility of a new pedestrian connection midblock on NE 94th St to provide a new walking route from 5th Ave NE to 1st Ave NE. This street currently dead ends. |  | Sidewalk | Low
29 | 29 | 3rd Ave NE - People Street | 3rd Ave NE (NE Northgate Way to NE 115th St) | Make 3rd Ave NE a People Street that prioritizes people walking, biking, and playing while still allowing vehicular travel. |  | PSPS | Medium
30 | 30 | 92nd St NE Multimodal Improvements | 92nd St NE (1st Ave NE to Wallingford Ave N) | This street is an important connection between the eastern and western sides of the regional center. Evaluate the roadway, especially at the I-5 overcrossing, for ways to prioritize walking, rolling, and biking and make it more comfortable. |  | Corridor | Medium

## List Options (hidden)
Chapter | Lead Department |  | Timeframe
Neighborhood for All Seasons | OPCD | Office of Planning and Community Development | Short-term | 0-5 years
Living with Place | SDOT | Seattle Department of Transportation | Medium-term | 6-15 years
Create Northgate | OH | Office of Housing | Long-term | 16+ years
Connected Communities | OSE | Office of Sustainability and the Environment | Ongoing
Shared Abundance | SPU | Seattle Public Utilities
| SCL | Seattle City Light
| SPR | Seattle Parks and Recreation
| ARTS | Office of Arts and Culture
| DON | Department of Neighborhoods
| OED | Office of Economic Development
SPL
SHA
SDCI
SFD
Mayor's Office
Sound Transit
King County Metro