## Sheet1
Seattle Department of Transportation
Bridging the Gap Planned Accomplishments
Year: 2013 | [5 empty] | Annual target has been met |  |  | 42 accomplishment types are green
Run Date:01/27/2014 | [5 empty] | Annual target is on track to be met |  |  | 0 accomplishment types are light green
Division: All | [5 empty] | Annual target is on track with caution |  |  | 0 accomplishment types are yellow
Program: All | [5 empty] | Annual target will not be met |  |  | 0 accomplishment types are red
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices evaluated | Count | 225 | 83 | 54 | 100 | 55 | 292
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices installed, modified or removed | Count | 50 | 13 | 17 | 37 | 19 | 86
Commuter Mobility | Policy and Planning |  | Transit Service | Secured transit hours | Maintain | 44000 | 0 | 0 | 0 | 44000 | 44000
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Speed watch trailer deployed | Times | 50 | 51 | 0 | 0 | 0 | 51
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Traffic control concerns evaluated | Count | 550 | 211 | 504 | 402 | 464 | 1581
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn improvements installed | Signalized Intersection | 3 | 0 | 1 | 0 | 2 | 3
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn signal improvements evaluated | Intersections | 25 | 11 | 6 | 10 | 10 | 37
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New signals installed | Count | 2 | 0 | 1 | 1 | 0 | 2
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New traffic signal requests evaluated | Count | 40 | 15 | 13 | 12 | 19 | 59
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Corridor and Intersection Improvements | Traffic Management |  | Collision Evaluation Program | Safety concerns investigated | Count | 30 | 10 | 3 | 5 | 15 | 33
Corridor and Intersection Improvements | Policy and Planning |  | Transit Corridor Projects | Transit corridor project implementation | Milestones | 7 | 0 | 0 | 2 | 5 | 7
Neighborhood Enhancements | Traffic Management |  | NSF/CRF neighborhood project implementation | Large neighborhood project implementation | Select Projects | TBD | 0 | 0 | 0 | 0 | Projects Selected
Neighborhoods | Traffic Management |  | Pedestrian Master Plan Implementation | Crossing improvements implemented | Count | 42 | 15 | 13 | 6 | 11 | 45
Neighborhoods | Traffic Management |  | Pedestrian Master Plan - School Safety | Walking routes to schools improved for safety | Number of Schools | 8 | 1 | 2 | 5 | 1 | 9
Roads | Capital Projects and Roadway Structures |  | Arterial Asphalt and Concrete Program | Roads paved | Lane miles | 12 | 0 | 0 | 0 | 19.7 | 19.7
Sidewalk Maintenance | Street Maintenance |  | Sidewalk Safety Repair | Sidewalks repaired | Block Equivalent | 25 | 2.37 | 6.66 | 7.21 | 8.9 | 25.14
Signal Major Maintenance | Traffic Management |  | Pedestrian Countdown Signals | Pedestrian Countdown signals installed | Intersections | 25 | 0 | 10 | 8 | 8 | 26
Signal Major Maintenance | Traffic Management |  | Signal Major Maintenance | Signal Major Maintenance Projects. | Count | 8 | 1 | 3 | 0 | 4 | 8
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Arterials restriped (plus edge lines) | Lane Line Miles | 850 | 7.19 | 331.74 | 445.7 | 83.13 | 867.76
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Crash cushions replaced | Count | 10 | 0 | 3 | 0 | 7 | 10
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Crosswalks remarked | Count | 500 | 7 | 216 | 224 | 161 | 608
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Guardrail replaced/installed | Linear feet | 700 | 113 | 339.5 | 86.75 | 335 | 874.25
Signs and Markings | Traffic Management |  | Sign Replacement Program | Regulatory street signs replaced | Count | 2000 | 782 | 798 | 828 | 851 | 3259
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Signs and Markings | Traffic Management |  | Pedestrian Master Plan - School Safety | Signage of School Zones Improved | Number of Schools | 10 | 1 | 4 | 6 | 0 | 11
Signs and Markings | Traffic Management |  | Sign Replacement Program | Street name signs replaced | Intersections | 1575 | 528 | 175 | 266 | 606 | 1575
Roads | Capital Projects and Roadway Structures |  | Arterial Major Maintenance | Lane miles of paving | Lane miles | 11 | 0 | 0 | 0 | 14 | 14
Structures Maintenance | Capital Projects and Roadway Structures |  | Bridge/Structure Maintenance | Bridge repair requests completed | Count | 190 | 40 | 21 | 29 | 143 | 233
Signs and Markings | Traffic Management |  | Sign Replacement Program | Directional signs replaced | Count | 5 | 0 | 0 | 0 | 5 | 5
Structures Maintenance | Capital Projects and Roadway Structures |  | Stairway/Structure Maintenance | Stairways rehabilitated | Count | 3 | 0 | 0 | 4 | 3 | 7
Traffic Signals | Traffic Management |  | Traffic Signal Operations | Traffic control cabinets replaced | Count | 6 | 0 | 0 | 0 | 6 | 6
Traffic Signals | Traffic Management |  | Traffic Signal Maintenance | Traffic signals maintained | Maintenance Events | 1024 | 222 | 44 | 313 | 445 | 1024
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Bicycle facility maintenance | Lane miles | 70 | 2.87 | 27.01 | 33.28 | 8.44 | 71.6
Trails and Bike Paths | Traffic Management |  | Bike Spot Safety Improvements | Bicycle parking (racks) | spaces | 400 | 58 | 164 | 10 | 188 | 420
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike lanes and sharrows striped | Miles | 7 | 0.2 | 1.35 | 3.58 | 2.55 | 7.68
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Greenways installed | Miles | 7.5 | 0 | 0 | 2.14 | 5.36 | 7.5
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike route signs installed | Miles of bike routes | 25 | 14.91 | 0 | 3.25 | 8.54 | 26.7
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan Implementation | Design and coordinate construction new curb ramps | Count | 130 | 41 | 19 | 8 | 65 | 133
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan Implementation | Sidewalks built | Block equivalent | 7 | 0 | 0 | 0 | 8.65 | 8.65
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Trail Inspection | Miles of trails | 40 | 40.1 | 0 | 0 | 0 | 40.1
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Urban trail and bikeway spot improvements | Count | 10 | 0 | 5 | 2 | 3 | 10
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Landscape Maintenance | Landscape maintenance | Maintenance Events | 840 | 132 | 278 | 380 | 298 | 1088
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees planted | Count | 600 | 84 | 403 | 0 | 169 | 656
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees pruned | Count | 3000 | 1048 | 325 | 831 | 1311 | 3515