## Sheet1
Seattle Department of Transportation
Bridging the Gap Planned Accomplishments
Year: 2012 | [5 empty] | Annual target has been met |  |  | 41 accomplishment types are green
Run Date: End of Year | [5 empty] | Annual target is on track to be met |  |  | 0 accomplishment types are light green
Division: All | [5 empty] | Annual target is on track with caution |  |  | 0 accomplishment types are yellow
Program: All | [5 empty] | Annual target will not be met |  |  | 1 accomplishment types are red
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices evaluated | Count | 225 | 85 | 66 | 44 | 62 | 257
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements - Signals | Electrical traffic control devices installed, modified or removed | Count | 50 | 33 | 52 | 6 | 5 | 96
Commuter Mobility | Policy and Planning |  | Transit Service | Secured transit hours | Maintain | 44000 | 0 | 0 | 44000 | 0 | 44000
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Speed watch trailer deployed | Times | 50 | 21 | 28 | 1 | 0 | 50
Commuter Mobility | Traffic Management |  | Traffic Operations Spot Improvements | Traffic control concerns evaluated | Count | 550 | 414 | 309 | 483 | 272 | 1478
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn improvements installed | Signalized Intersection | 3 | 0 | 1 | 1 | 1 | 3
Corridor and Intersection Improvements | Traffic Management |  | Left Turn Signals (auto related) | Left turn signal improvements evaluated | Intersections | 30 | 19 | 4 | 3 | 13 | 39
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New signals installed | Count | 2 | 0 | 0 | 0 | 2 | 2
Corridor and Intersection Improvements | Traffic Management |  | New Traffic Signals | New traffic signal requests evaluated | Count | 50 | 14 | 14 | 14 | 13 | 55
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Corridor and Intersection Improvements | Traffic Management |  | Collision Evaluation Program | Safety concerns investigated | Count | 30 | 9 | 7 | 6 | 10 | 32
Corridor and Intersection Improvements | Policy and Planning |  | Transit Corridor Projects | Transit corridor project implementation | Milestones | 4 | 0 | 0 | 3 | 1 | 4
Neighborhood Enhancements | Traffic Management |  | NSF/CRF neighborhood project implementation | Large neighborhood project implementation | Construct projects | 8 | 0 | 1 | 4 | 3 | 8
Neighborhoods | Traffic Management |  | Pedestrian Master Plan Implementation | Crossing improvements implemented | Count | 42 | 4 | 4 | 12 | 27 | 47
Neighborhoods | Traffic Management |  | Pedestrian Master Plan - School Safety | Walking routes to schools improved for safety | Number of Schools | 5 | 2 | 1 | 3 | 0 | 6
Roads | Capital Projects and Roadway Structures |  | Arterial Asphalt and Concrete Program | Roads paved | Lane miles | 15 | 0 | 0 | 0 | 15 | 15
Sidewalk Maintenance | Street Maintenance |  | Sidewalk Safety Repair | Sidewalks repaired | Block Equivalent | 22 | 4.33 | 2.78 | 15.8 | 1.42 | 24.33
Signal Major Maintenance | Traffic Management |  | Pedestrian Countdown Signals | Pedestrian Countdown signals installed | Intersections | 25 | 11 | 4 | 3 | 7 | 25
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Arterials restriped (plus edge lines) | Lane Line Miles | 945 | 28.1 | 337.44 | 449.81 | 129.76 | 945.11
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Crash cushions replaced | Count | 2 | 1 | 0 | 0 | 1 | 2
Signs and Markings | Traffic Management |  | Curb and Pavement Marking | Crosswalks remarked | Count | 500 | 19 | 159 | 288 | 35 | 501
Signs and Markings | Traffic Management |  | Guardrail and Crash Cushion Rehabilitation | Guardrail replaced/installed | Linear feet | 1886 | 1147.5 | 214.5 | 0 | 572 | 1934
Signs and Markings | Traffic Management |  | Sign Replacement Program | Regulatory street signs replaced | Count | 2000 | 888 | 700 | 938 | 455 | 2981
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Signs and Markings | Traffic Management |  | Pedestrian Master Plan - School Safety | Signage of School Zones Improved | Number of Schools | 10 | 5 | 4 | 2 | 0 | 11
Signs and Markings | Traffic Management |  | Sign Replacement Program | Street name signs replaced | Intersections | 1575 | 807 | 200 | 1 | 576 | 1584
Roads | Capital Projects and Roadway Structures |  | Arterial Major Maintenance | Lane miles of paving | Lane miles | 7.1 | 0 | 3 | 4 | 0 | 7
Structures Maintenance | Capital Projects and Roadway Structures |  | Bridge/Structure Maintenance | Bridge repair requests completed | Count | 168 | 127 | 58 | 75 | 21 | 281
Bridges and Structures | Capital Projects and Roadway Structures |  | Bridge Painting | Bridges painted | Count | 2 | 1 | 1 | 0 | 0 | 2
Structures Maintenance | Capital Projects and Roadway Structures |  | Stairway/Structure Maintenance | Stairways rehabilitated | Count | 3 | 0 | 0 | 3 | 1 | 4
Traffic Signals | Traffic Management |  | Traffic Signal Operations | Traffic control cabinets replaced | Count | 6 | 2 | 0 | 0 | 6 | 8
Traffic Signals | Traffic Management |  | Traffic Signal Maintenance | Traffic signals maintained | Maintenance Events | 1060 | 216 | 265 | 312 | 269 | 1062
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Bicycle facility maintenance | Lane miles | 40 | 5.71 | 15.42 | 18.9 | 0 | 40.03
Trails and Bike Paths | Traffic Management |  | Bike Spot Safety Improvements | Bicycle parking (racks) | spaces | 600 | 128 | 180 | 0 | 300 | 608
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike lanes and sharrows striped | Miles | 15 | 0 | 2 | 5.97 | 7.24 | 15.21
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Greenways installed | Miles | 7 | 0 | 0.9 | 0 | 0 | 0.9
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Bike route signs installed | Miles of bike routes | 30 | 19.1 | 0 | 0 | 13.47 | 32.57
Program | Division | Project # | Project Name | Accomplishment | Unit of Measure | Work Plan Target | Q1 Total | Q2 Total | Q3 Total | Q4 Total | YTD Total
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan Implementation | Design and coordinate construction new curb ramps | Count | 150 | 37 | 43 | 40 | 37 | 157
Trails and Bike Paths | Traffic Management |  | Pedestrian Master Plan Implementation | Sidewalks built | Block equivalent | 12 | 4.4 | 0 | 0 | 7.8 | 12.2
Trails and Bike Paths | Traffic Management |  | Bike Master Plan Implementation | Trail Inspection | Miles of trails | 35 | 35.5 | 0 | 0 | 0 | 35.5
Trails and Bike Paths | Traffic Management |  | Urban Trail and Bikeway Spot Improvements | Urban trail and bikeway spot improvements | Count | 10 | 5 | 1 | 3 | 1 | 10
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Landscape Maintenance | Landscape maintenance | Maintenance Events | 840 | 116 | 221 | 281 | 352 | 970
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees planted | Count | 700 | 190 | 236 | 0 | 389 | 815
Tree and Landscape Maintenance | Street Use and Urban Forestry |  | Arborist Service | Trees pruned | Count | 3000 | 314 | 375 | 1469 | 941 | 3099